## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Santhosh Kumar | 2026-07-02 | Atlas failed to classify unsupported input | Sprint 1 | Santhosh Kumar | Functional | Added input validation and mode detection | 2026-07-03 | Closed | Resolved
2 | Santhosh Kumar | 2026-07-05 | Vault state not shared correctly between agents | Sprint 1 | Santhosh Kumar | Functional | Implemented centralized Vault object | 2026-07-06 | Closed | Resolved
3 | Santhosh Kumar | 2026-07-09 | LangGraph routing configuration issue | Sprint 1 | Santhosh Kumar | Configuration | Updated graph routing logic | 2026-07-10 | Closed | Resolved
4 | Santhosh Kumar | 2026-07-14 | Tavily API request failed during web search | Sprint 2 | Santhosh Kumar | API Integration | Added exception handling and retry-safe logic | 2026-07-15 | Closed | Resolved
5 | Santhosh Kumar | 2026-07-16 | Invalid PDF caused pipeline crash | Sprint 2 | Santhosh Kumar | Functional | Added FileNotFound and PDF parsing validation | 2026-07-17 | Closed | Resolved
6 | Santhosh Kumar | 2026-07-18 | Gemini API quota exceeded | Sprint 2 | Santhosh Kumar | API Integration | Shifted Pathfinder and Scribe to Groq while retaining Gemini embeddings | 2026-07-19 | Closed | Resolved
7 | Santhosh Kumar | 2026-07-20 | ChromaDB similarity search returned no results | Sprint 2 | Santhosh Kumar | Functional | Added validation before synthesis | 2026-07-21 | Closed | Resolved
8 | Santhosh Kumar | 2026-07-21 | Empty LLM response from Pathfinder | Sprint 2 | Santhosh Kumar | Functional | Introduced PathfinderError handling | 2026-07-22 | Closed | Resolved
9 | Santhosh Kumar | 2026-07-22 | Empty synthesis generated | Sprint 2 | Santhosh Kumar | Functional | Added Synthesizer validation checks | 2026-07-23 | Closed | Resolved
10 | Santhosh Kumar | 2026-07-23 | Empty report generated by Scribe | Sprint 2 | Santhosh Kumar | Functional | Added Scribe response validation | 2026-07-24 | Closed | Resolved
11 | Santhosh Kumar | 2026-07-24 | Pipeline terminated unexpectedly on runtime errors | Sprint 2 | Santhosh Kumar | Functional | Added centralized exception handling in main.py | 2026-07-25 | Closed | Resolved
12 | Santhosh Kumar | 2026-07-25 | Missing environment variables not detected | Sprint 2 | Santhosh Kumar | Configuration | Added startup validation for API keys | 2026-07-26 | Closed | Resolved
13 | Santhosh Kumar | 2026-07-28 | Communication between agents not traceable | Sprint 3 | Santhosh Kumar | Functional | Added centralized communication log | 2026-07-29 | Closed | Resolved
14 | Santhosh Kumar | 2026-07-30 | ChromaDB stored duplicate knowledge | Sprint 3 | Santhosh Kumar | Functional | Improved metadata handling | 2026-07-31 | Closed | Resolved
15 | Santhosh Kumar | 2026-07-31 | Long-term retrieval returned unrelated chunks | Sprint 3 | Santhosh Kumar | Functional | Added relevance score filtering | 2026-08-01 | Closed | Resolved
16 | Santhosh Kumar | 2026-08-02 | Empty long-term memory caused retrieval issues | Sprint 3 | Santhosh Kumar | Functional | Added graceful fallback | 2026-08-03 | Closed | Resolved
17 | Santhosh Kumar | 2026-08-04 | Workflow execution lacked validation evidence | Sprint 3 | Santhosh Kumar | Functional | Implemented workflow_validator.py | 2026-08-05 | Closed | Resolved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others